## READ ME
India Labor Arbitrage Program — Monthly Consolidation Workbook
PURPOSE
Single consolidation file for the India GCC ramp-up program. Each org finance partner updates their own Org tab monthly; the Consolidation and Dashboard tabs roll up automatically.
HOW TO SET UP (owner, one time)
1. Go to the Setup tab and replace 'Org 1 — REPLACE' etc. with the real organization names. Every tab picks the names up automatically.
2. Optionally rename the Org_1..Org_8 sheet tabs to match — Excel updates all formulas automatically when a sheet is renamed.
3. Replace the ILLUSTRATIVE placeholder numbers on the Targets tab with the committed monthly baseline you distributed to each org (yellow cells).
4. Org_1 contains EXAMPLE actuals for Jan–Mar 2026 to demonstrate the mechanics — clear them before first use.
HOW TO SUBMIT (org finance partners, monthly)
1. Open your org's tab. Enter values in BLUE cells only for the month just closed.
2. GREEN cells are filled centrally from PlanIt/HR — do not overwrite unless asked.
3. GREY cells are your committed targets, linked from the Targets tab — never edit on this tab.
4. Set the month's RAG status, answer the leakage attestation, and add commentary if any headline metric misses target materially. Enter your name in the 'Attested by' row.
5. Submissions are due workday 3; consolidation is published workday 5. (Placeholder — confirm.)
RULES
What counts as labor arbitrage savings (and what doesn't) is defined on the Guiding Principles tab. Read it before your first submission. When in doubt, ask central program finance BEFORE reporting a number.
DO NOT
• Insert new sheets between Org_1 and Org_8 (the consolidation ranges span those tabs).
• Add or delete rows/columns on Org tabs — the consolidation reads fixed positions.
• Net one-time transition costs into your reduction numbers — report them on their own row.
COLOR KEY
BLUE = org enters data ¦ GREEN = central fill (PlanIt/HR) ¦ GREY = linked target (do not edit) ¦ YELLOW = placeholder to replace during setup

## Setup
Setup — organization names and lists
REPLACE the names below with your 8 organizations. All tabs reference these cells.
Org tab Org_1 display name: | Org 1 — REPLACE
Org tab Org_2 display name: | Org 2 — REPLACE
Org tab Org_3 display name: | Org 3 — REPLACE
Org tab Org_4 display name: | Org 4 — REPLACE
Org tab Org_5 display name: | Org 5 — REPLACE
Org tab Org_6 display name: | Org 6 — REPLACE
Org tab Org_7 display name: | Org 7 — REPLACE
Org tab Org_8 display name: | Org 8 — REPLACE
Dropdown lists (used by data validation):
RAG: | Green
Amber
Red
Yes/No: | Y
N

## Targets
Committed monthly baseline by organization
ILLUSTRATIVE PLACEHOLDERS — replace every yellow cell with the committed baseline distributed to the orgs. Baseline changes only via approved change request.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
India hires (heads) |  | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 38 | 75 | 112 | 150 | 188 | 225 | 262 | 300 | 338 | 375 | 412 | 450 | 488 | 525 | 562 | 600 | 638 | 675 | 712 | 750 | 788 | 825 | 862 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225 | 240 | 255 | 270 | 285 | 300 | 315 | 330 | 345 | 360 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156 | 168 | 180 | 192 | 204 | 216 | 228 | 240 | 252 | 264 | 276 | 288 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12 | 18 | 24 | 30 | 36 | 42 | 48 | 54 | 60 | 66 | 72 | 78 | 84 | 90 | 96 | 102 | 108 | 114 | 120 | 126 | 132 | 138 | 144 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
India cost adds ($K) |  | 34 | 68 | 101 | 135 | 169 | 202 | 236 | 270 | 304 | 338 | 371 | 405 | 461 | 518 | 574 | 630 | 686 | 742 | 799 | 855 | 911 | 968 | 1024 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080
Net labor arbitrage ($K)
India hires (heads) |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 32 | 65 | 98 | 130 | 162 | 195 | 228 | 260 | 292 | 325 | 358 | 390 | 422 | 455 | 488 | 520 | 552 | 585 | 618 | 650 | 682 | 715 | 748 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780 | 780
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 26 | 39 | 52 | 65 | 78 | 91 | 104 | 117 | 130 | 143 | 156 | 169 | 182 | 195 | 208 | 221 | 234 | 247 | 260 | 273 | 286 | 299 | 312 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 21 | 31 | 42 | 52 | 62 | 73 | 83 | 94 | 104 | 114 | 125 | 135 | 146 | 156 | 166 | 177 | 187 | 198 | 208 | 218 | 229 | 239 | 250 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 16 | 21 | 26 | 31 | 36 | 42 | 47 | 52 | 57 | 62 | 68 | 73 | 78 | 83 | 88 | 94 | 99 | 104 | 109 | 114 | 120 | 125 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
India cost adds ($K) |  | 30 | 60 | 90 | 120 | 150 | 180 | 210 | 240 | 270 | 300 | 330 | 360 | 409 | 458 | 506 | 555 | 604 | 652 | 701 | 750 | 799 | 848 | 896 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945
Net labor arbitrage ($K)
India hires (heads) |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 30 | 60 | 90 | 120 | 150 | 180 | 210 | 240 | 270 | 300 | 330 | 360 | 390 | 420 | 450 | 480 | 510 | 540 | 570 | 600 | 630 | 660 | 690 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156 | 168 | 180 | 192 | 204 | 216 | 228 | 240 | 252 | 264 | 276 | 288 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 19 | 29 | 38 | 48 | 58 | 67 | 77 | 86 | 96 | 106 | 115 | 125 | 134 | 144 | 154 | 163 | 173 | 182 | 192 | 202 | 211 | 221 | 230 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 14 | 19 | 24 | 29 | 34 | 38 | 43 | 48 | 53 | 58 | 62 | 67 | 72 | 77 | 82 | 86 | 91 | 96 | 101 | 106 | 110 | 115 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
India cost adds ($K) |  | 26 | 52 | 79 | 105 | 131 | 158 | 184 | 210 | 236 | 262 | 289 | 315 | 360 | 405 | 450 | 495 | 540 | 585 | 630 | 675 | 720 | 765 | 810 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855 | 855
Net labor arbitrage ($K)
India hires (heads) |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 28 | 55 | 82 | 110 | 138 | 165 | 193 | 220 | 248 | 275 | 302 | 330 | 358 | 385 | 413 | 440 | 468 | 495 | 522 | 550 | 578 | 605 | 632 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 55 | 66 | 77 | 88 | 99 | 110 | 121 | 132 | 143 | 154 | 165 | 176 | 187 | 198 | 209 | 220 | 231 | 242 | 253 | 264 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 26 | 35 | 44 | 53 | 62 | 70 | 79 | 88 | 97 | 106 | 114 | 123 | 132 | 141 | 150 | 158 | 167 | 176 | 185 | 194 | 202 | 211 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 13 | 18 | 22 | 26 | 31 | 35 | 40 | 44 | 48 | 53 | 57 | 62 | 66 | 70 | 75 | 79 | 84 | 88 | 92 | 97 | 101 | 106 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110
India cost adds ($K) |  | 26 | 52 | 79 | 105 | 131 | 158 | 184 | 210 | 236 | 262 | 289 | 315 | 356 | 398 | 439 | 480 | 521 | 562 | 604 | 645 | 686 | 728 | 769 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810 | 810
Net labor arbitrage ($K)
India hires (heads) |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 125 | 150 | 175 | 200 | 225 | 250 | 275 | 300 | 325 | 350 | 375 | 400 | 425 | 450 | 475 | 500 | 525 | 550 | 575 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110 | 120 | 130 | 140 | 150 | 160 | 170 | 180 | 190 | 200 | 210 | 220 | 230 | 240 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 24 | 32 | 40 | 48 | 56 | 64 | 72 | 80 | 88 | 96 | 104 | 112 | 120 | 128 | 136 | 144 | 152 | 160 | 168 | 176 | 184 | 192 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 36 | 40 | 44 | 48 | 52 | 56 | 60 | 64 | 68 | 72 | 76 | 80 | 84 | 88 | 92 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
India cost adds ($K) |  | 22 | 45 | 68 | 90 | 112 | 135 | 158 | 180 | 202 | 225 | 248 | 270 | 308 | 345 | 382 | 420 | 458 | 495 | 532 | 570 | 608 | 645 | 682 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720 | 720
Net labor arbitrage ($K)
India hires (heads) |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 22 | 45 | 68 | 90 | 112 | 135 | 158 | 180 | 202 | 225 | 248 | 270 | 292 | 315 | 338 | 360 | 382 | 405 | 428 | 450 | 472 | 495 | 518 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 54 | 63 | 72 | 81 | 90 | 99 | 108 | 117 | 126 | 135 | 144 | 153 | 162 | 171 | 180 | 189 | 198 | 207 | 216 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 22 | 29 | 36 | 43 | 50 | 58 | 65 | 72 | 79 | 86 | 94 | 101 | 108 | 115 | 122 | 130 | 137 | 144 | 151 | 158 | 166 | 173 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 11 | 14 | 18 | 22 | 25 | 29 | 32 | 36 | 40 | 43 | 47 | 50 | 54 | 58 | 61 | 65 | 68 | 72 | 76 | 79 | 83 | 86 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
India cost adds ($K) |  | 19 | 38 | 56 | 75 | 94 | 112 | 131 | 150 | 169 | 188 | 206 | 225 | 259 | 292 | 326 | 360 | 394 | 428 | 461 | 495 | 529 | 562 | 596 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630 | 630
Net labor arbitrage ($K)
India hires (heads) |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 18 | 35 | 52 | 70 | 88 | 105 | 122 | 140 | 158 | 175 | 192 | 210 | 227 | 245 | 262 | 280 | 298 | 315 | 332 | 350 | 368 | 385 | 402 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 91 | 98 | 105 | 112 | 119 | 126 | 133 | 140 | 147 | 154 | 161 | 168 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 17 | 22 | 28 | 34 | 39 | 45 | 50 | 56 | 62 | 67 | 73 | 78 | 84 | 90 | 95 | 101 | 106 | 112 | 118 | 123 | 129 | 134 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 8 | 11 | 14 | 17 | 20 | 22 | 25 | 28 | 31 | 34 | 36 | 39 | 42 | 45 | 48 | 50 | 53 | 56 | 59 | 62 | 64 | 67 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
India cost adds ($K) |  | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 206 | 232 | 259 | 285 | 311 | 338 | 364 | 390 | 416 | 442 | 469 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495 | 495
Net labor arbitrage ($K)
India hires (heads) |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reductions — Professional services ($K) |  | 0 | 0 | 0 | 0 | 8 | 15 | 22 | 30 | 38 | 45 | 52 | 60 | 68 | 75 | 82 | 90 | 98 | 105 | 112 | 120 | 128 | 135 | 142 | 150 | 158 | 165 | 172 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180
Reductions — Offshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
Reductions — Onshore contractors ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 7 | 10 | 12 | 14 | 17 | 19 | 22 | 24 | 26 | 29 | 31 | 34 | 36 | 38 | 41 | 43 | 46 | 48 | 50 | 53 | 55 | 58 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Reductions — Employees / Other ($K) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12 | 13 | 14 | 16 | 17 | 18 | 19 | 20 | 22 | 23 | 24 | 25 | 26 | 28 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
India cost adds ($K) |  | 8 | 15 | 22 | 30 | 38 | 45 | 52 | 60 | 68 | 75 | 82 | 90 | 101 | 112 | 124 | 135 | 146 | 158 | 169 | 180 | 191 | 202 | 214 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225
Net labor arbitrage ($K)

## Org_1
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt) | 2026-01-01: 5; 2026-02-01: 6; 2026-03-01: 6
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt) | 2026-01-01: 45; 2026-02-01: 45; 2026-03-01: 45
Avg India loaded comp — Actual | $K/yr · central (PlanIt) | 2026-01-01: 44; 2026-02-01: 46; 2026-03-01: 47
India attrition in month | heads · central (HR) | 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 1
% of India hires fully productive | % · org input | 2026-01-01: 0%; 2026-02-01: 20%; 2026-03-01: 40%
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input | 2026-01-01: 0; 2026-02-01: 20; 2026-03-01: 45
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input | 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 10
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input | 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 5
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input | 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input | 2026-01-01: 0; 2026-02-01: 1; 2026-03-01: 3
Exit run-rate of reductions (annualized) | $K · org input | 2026-01-01: 0; 2026-02-01: 240; 2026-03-01: 720
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input | 2026-01-01: 19; 2026-02-01: 41; 2026-03-01: 64
One-time transition costs (memo — never net) | $K · org input | 2026-01-01: 35; 2026-02-01: 15; 2026-03-01: 10
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input | 2026-01-01: Green; 2026-02-01: Green; 2026-03-01: Amber
Attest: reductions free of leakage? | Y/N · org input | bar: 2026-01-01 to 2026-03-01
Attested by (org finance partner) | name · org input | 2026-01-01: A. Partner; 2026-02-01: A. Partner; 2026-03-01: A. Partner
Commentary (required on material variance) | text · org input | 2026-03-01: Prof services roll-off slipped ~1 month; recovery expected Apr.

## Org_2
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt)
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt)
Avg India loaded comp — Actual | $K/yr · central (PlanIt)
India attrition in month | heads · central (HR)
% of India hires fully productive | % · org input
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input
Exit run-rate of reductions (annualized) | $K · org input
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input
One-time transition costs (memo — never net) | $K · org input
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input
Attest: reductions free of leakage? | Y/N · org input
Attested by (org finance partner) | name · org input
Commentary (required on material variance) | text · org input

## Org_3
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt)
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt)
Avg India loaded comp — Actual | $K/yr · central (PlanIt)
India attrition in month | heads · central (HR)
% of India hires fully productive | % · org input
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input
Exit run-rate of reductions (annualized) | $K · org input
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input
One-time transition costs (memo — never net) | $K · org input
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input
Attest: reductions free of leakage? | Y/N · org input
Attested by (org finance partner) | name · org input
Commentary (required on material variance) | text · org input

## Org_4
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt)
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt)
Avg India loaded comp — Actual | $K/yr · central (PlanIt)
India attrition in month | heads · central (HR)
% of India hires fully productive | % · org input
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input
Exit run-rate of reductions (annualized) | $K · org input
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input
One-time transition costs (memo — never net) | $K · org input
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input
Attest: reductions free of leakage? | Y/N · org input
Attested by (org finance partner) | name · org input
Commentary (required on material variance) | text · org input

## Org_5
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt)
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt)
Avg India loaded comp — Actual | $K/yr · central (PlanIt)
India attrition in month | heads · central (HR)
% of India hires fully productive | % · org input
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input
Exit run-rate of reductions (annualized) | $K · org input
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input
One-time transition costs (memo — never net) | $K · org input
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input
Attest: reductions free of leakage? | Y/N · org input
Attested by (org finance partner) | name · org input
Commentary (required on material variance) | text · org input

## Org_6
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt)
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt)
Avg India loaded comp — Actual | $K/yr · central (PlanIt)
India attrition in month | heads · central (HR)
% of India hires fully productive | % · org input
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input
Exit run-rate of reductions (annualized) | $K · org input
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input
One-time transition costs (memo — never net) | $K · org input
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input
Attest: reductions free of leakage? | Y/N · org input
Attested by (org finance partner) | name · org input
Commentary (required on material variance) | text · org input

## Org_7
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt)
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt)
Avg India loaded comp — Actual | $K/yr · central (PlanIt)
India attrition in month | heads · central (HR)
% of India hires fully productive | % · org input
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input
Exit run-rate of reductions (annualized) | $K · org input
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input
One-time transition costs (memo — never net) | $K · org input
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input
Attest: reductions free of leakage? | Y/N · org input
Attested by (org finance partner) | name · org input
Commentary (required on material variance) | text · org input

## Org_8
Enter BLUE cells only. GREEN = central fill. GREY = linked target (do not edit). See READ ME + Guiding Principles tabs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING
India hires — Target | heads · linked
India hires — Actual | heads · central (PlanIt)
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · central (PlanIt)
Avg India loaded comp — Actual | $K/yr · central (PlanIt)
India attrition in month | heads · central (HR)
% of India hires fully productive | % · org input
B. GROSS REDUCTIONS REALIZED IN PERIOD
Professional services — Target | $K · linked
Professional services — Actual | $K · org input
Offshore contractors — Target | $K · linked
Offshore contractors — Actual | $K · org input
Onshore contractors — Target | $K · linked
Onshore contractors — Actual | $K · org input
Employees / Other — Target | $K · linked
Employees / Other — Actual | $K · org input
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · org input
Exit run-rate of reductions (annualized) | $K · org input
C. INDIA COST ADDS
India loaded cost adds — Target | $K · linked
India loaded cost adds — Actual | $K · org input
One-time transition costs (memo — never net) | $K · org input
D. NET LABOR ARBITRAGE (B − C)
Net labor arbitrage — Target | $K · linked
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY
Overall RAG status for month | G/A/R · org input
Attest: reductions free of leakage? | Y/N · org input
Attested by (org finance partner) | name · org input
Commentary (required on material variance) | text · org input

## Consolidation
Program consolidation — all organizations
All values calculated. Numeric rows sum across Org_1..Org_8; comp and % rows are simple averages across orgs.
|  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
A. INDIA HIRING | · auto
India hires — Target | heads · auto
India hires — Actual | heads · auto
Cumulative hires — Target | heads · auto
Cumulative hires — Actual | heads · auto
Hires variance (Actual − Target), cumulative | heads · auto
Avg India loaded comp — Plan | $K/yr · auto
Avg India loaded comp — Actual | $K/yr · auto
India attrition in month | heads · auto
% of India hires fully productive | % · auto
B. GROSS REDUCTIONS REALIZED IN PERIOD | · auto
Professional services — Target | $K · auto
Professional services — Actual | $K · auto
Offshore contractors — Target | $K · auto
Offshore contractors — Actual | $K · auto
Onshore contractors — Target | $K · auto
Onshore contractors — Actual | $K · auto
Employees / Other — Target | $K · auto
Employees / Other — Actual | $K · auto
Total gross reductions — Target | $K · auto
Total gross reductions — Actual | $K · auto
Gross reductions variance | $K · auto
Headcount reduced in month — Actual | heads · auto
Exit run-rate of reductions (annualized) | $K · auto
C. INDIA COST ADDS | · auto
India loaded cost adds — Target | $K · auto
India loaded cost adds — Actual | $K · auto
One-time transition costs (memo — never net) | $K · auto
D. NET LABOR ARBITRAGE (B − C) | · auto
Net labor arbitrage — Target | $K · auto
Net labor arbitrage — Actual | $K · auto
Net variance (Actual − Target) | $K · auto
Cumulative net arbitrage — Target | $K · auto
Cumulative net arbitrage — Actual | $K · auto
E. STATUS, ATTESTATION & COMMENTARY | · auto
Overall RAG status for month | see org tabs / Dashboard
Attest: reductions free of leakage? | see org tabs / Dashboard
Attested by (org finance partner) | see org tabs / Dashboard
Commentary (required on material variance) | see org tabs / Dashboard

## Dashboard
India Labor Arbitrage Program — Executive Dashboard
PROGRAM KPIs (inception-to-date over all entered months)
Cumulative India hires — Target (program)
Cumulative India hires — Actual (program)
Net labor arbitrage ITD — Target ($K)
Net labor arbitrage ITD — Actual ($K)
Exit run-rate of reductions, latest reported ($K annualized)
ANNUAL SUMMARY
| 2026 | 2027 | 2028 | 2029
India hires — Target (heads)
India hires — Actual (heads)
Gross reductions — Target ($K)
Gross reductions — Actual ($K)
India cost adds — Actual ($K)
One-time transition costs ($K)
Net labor arbitrage — Target ($K)
Net labor arbitrage — Actual ($K)
MONTHLY TREND — NET LABOR ARBITRAGE ($K) |  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
Metric | Unit / who fills | time axis 2026-01-01 to 2029-12-01
Net arbitrage — Target
Net arbitrage — Actual
Cumulative — Target
Cumulative — Actual
RAG STATUS BY ORGANIZATION

## Guiding Principles
Guiding Principles — condensed (full draft: Guiding_Principles_DRAFT.md)
1. The baseline is the committed monthly target loaded to your forecast. Variances are vs. that baseline — never vs. prior year or re-forecast. Baseline moves only via approved change request.
2. A reduction COUNTS only if it is (a) labor cost in a committed category — professional services, managed/outsourced labor, offshore or onshore contractors, in-scope employees; (b) causally tied to the India transition; (c) realized and visible in the GL; and (d) run-rate in nature.
3. What does NOT count: software license or any non-labor favorability; one-time credits or rebates; rate renegotiations unrelated to transitioned volume; timing deferrals; unrelated vacancy savings; anything already claimed by another initiative (no double counting).
4. NO SUBSTITUTION: a labor-reduction shortfall may not be offset with unrelated favorability. Example: on-track India hiring + $500K prof services miss + $500K software favorability is reported as a $500K program miss, with commentary and recovery plan.
5. Report NET: gross reductions minus India loaded cost adds. One-time transition costs go on their own row and are never netted into reductions or run-rate.
6. Recognize savings in the month the run-rate reduction first hits the GL — not at contract signature or vendor notification. Partial months pro rata.
7. No leakage: a reduction is not real if equivalent spend reappears in another cost center, vendor, or expense line. You attest to this monthly.
8. Attestation & evidence: the org finance partner attests each submission and can identify the cost center and expense line for material reductions on request. Quarterly sample testing and true-up apply.
9. When in doubt, ask central program finance BEFORE reporting the number. Interpretation rulings are appended to the full Guiding Principles document.